## Sheet1
기간 | 주제 | 교재
1월 1주(12/31-1/6) | CIS (SK hynix - white pixel)
1월 2주(1/7-1/13) | 일본 여행(1/7-1/12)
1월 3주(1/14-1/20) | LASER Basic | Mai-Tai manual
1월 4주(1/21-1/27) | THz Generation, Detection 이해
2월 1주(1/28-2/3) | Optical Component 이해, Maintenace&표준화
2월 2주(2/4-2/10) | Lock-in amplifier 이해, Maintenace&표준화 | SR830 manual
2월 3주(2/11-2/17) | THz-TDS 이해, Maintenace&표준화
Jobs | Details |  | Duration
TDS Alignment | IR part + Delay line alignment |  | 1 week | 3.5 weeks
| THz part |  | 1 week
| THz detection |  | 0.5 week
| Maximizing (fine alingment) |  | 1 week
TDS LabVIEW | TDS LabVIEW standard program |  | 2 days | 2 weeks
| Company Devices | Newport and Applet | 1 day
|  | PI and PI library | 1 day
|  | Equip.Sol and RS232 | 1 day
|  | SmarAct and SA Library | 1 day
|  | Thorlabs and ActiveX | 1 day
| Integrated new devices into standard program |  | 0.5 week
TDS Experiment | Experiment condition: Dry air flow, dew point |  | 1 day | 0.5 week
| Monitoring: PSD and Tem/humidity sensors |  | 2 day

## Sheet2
No. | Item | Specific target |  | Jan 1st wk. | Jan 2nd wk. | Jan 3rd wk. | Jan 4th wk. | Feb 1st wk. | Feb 2nd wk. | Feb 3rd wk. | Feb 4th wk. | Feb 5th wk.
1 | SK Hynix (FDTD simulation) | Optimization of CIS basic structure (0.9 um) |  |  | 일 본 여 행
2 |  | Optimization of CIS structure based on hynix model
3 |  | New concept of CIS structure
4 |  | Preparation for presentation
5 | THz-TDS (Theory) | THz Generation & Detection (PC antenna)
6 |  | Lock-in-amplifier
7 |  | Training project
8 | Maintainance | Femtosecond Laser (MaiTai, Fusion)
9 |  | Dry-air generator
10 |  | Management of humidity & temperature in lab.
11 |  | Positions of equipment & samples
12 |  | Optical components
13 | Software | Labview | Basic of Labview
14 |  |  | Introduction of subvi & GPIB
15 |  |  | Labview stage communication
16 |  | THz-TDS system
17 |  | Basic of Solidworks & Optisworks
18 |  | Basic of COMSOL
19 | THz-TDS (Experiment) | Mirror & Parabolic mirror align
20 |  | Mrrior on motorized stages align
21 |  | Detector align
22 |  | THz maximization
23 |  | THz signal acquisition